## Slide 1
12-MONTH ADVENTURE
JCorp x Copilot
Let's make work magical.
A 12-month, remote-first M365 Copilot enablement program for Johor Corporation HQ.
Delivered live from Microsoft Kuala Lumpur.
Prepared for Johor Corporation | By Microsoft Malaysia

## Slide 2
EXECUTIVE SUMMARY
A 12-month program to skill 200 JCorp employees
Remote-first delivery from Microsoft KL with executive on-site touchpoints
200
JCorp HQ employees
12 mo
Four phased quests
75%
Weekly active target
85%
Sessions delivered remotely
Why this plan
JCorp's 200 HQ employees are a high-leverage population to demonstrate measurable productivity gains. The Johor-KL gap makes a remote-first cadence the only sustainable model. On-site time is reserved for executive sponsorship and milestone events that genuinely require physical presence.
Outcomes by month 12
75% of licensed users active weekly
10+ documented JCorp use cases with measured value
15-person internal champions network sustaining adoption
Executive scorecard tracked quarterly by JCorp leadership
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
2

## Slide 3
THE OPPORTUNITY
Why M365 Copilot, why now for JCorp
Productivity is the new competitive moat
Enterprises deploying generative AI report 30-50% time savings on document, analytics, and communication tasks. JCorp's HQ functions are highly information-intensive - prime ground for compounding gains.
Microsoft 365 is already your foundation
Copilot extends the M365 environment JCorp already trusts and pays for. No net-new platform risk, no new vendors, no data residency surprise.
200 HQ employees is the right size to win
Large enough to demonstrate enterprise-grade outcomes. Small enough to instrument carefully and personalise the journey for each function.
The window is now
Peer Malaysian conglomerates are deploying Copilot in 2026. Moving deliberately this year positions JCorp as a regional reference customer.
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
3

## Slide 4
OUR VISION
By month 12, every JCorp
teammate has an AI sidekick.
Drafting board papers in minutes. Summarising meetings before the door closes.
Analysing subsidiary performance over a coffee. Asking the company's knowledge a question, in plain English, and getting a real answer.
That's the vibe. Let's go build it together.

## Slide 5
AUDIENCE
200 employees, 5 personas, tailored journeys
Chart: 
| Knowledge Workers | People Managers | Specialists | Champions | Executive Leaders
Persona | 120 | 30 | 25 | 15 | 10
Persona | Users | Focus
Executive Leaders | 10 | Strategic decision support, exec briefings
People Managers | 30 | Team productivity, meeting summarisation
Knowledge Workers | 120 | Daily Office productivity, drafting
Specialists | 25 | Excel analytics, contract review, policy
Champions | 15 | Advanced use cases, peer coaching
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
5

## Slide 6
DELIVERY MODEL
Remote-first by design - the Johor-KL gap, solved
Microsoft is in KL. JCorp HQ is in Johor. We engineered the program around that reality from day one.
Default to virtual
Live virtual labs (max 25 learners), Teams Live Events, on-demand Microsoft Learn. Capped at 60 min per session - no fatigue.
Travel for impact, not for routine
JCorp Senior Leadership immerses at Microsoft KL Executive Briefing Centre quarterly - more impactful than any Johor site visit.
Microsoft visits Johor 3 times in 12 months
Launch party (M1), mid-year roadshow (M8), grand finale (M12). Each visit has a virtual fallback plan.
Champions bridge the distance
15 internal champions are the always-on presence between virtual sessions. They coach peers and keep momentum local.
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
6

## Slide 7
CHANNEL MIX
85% remote, 12% Microsoft KL, 3% on-site Johor
Chart: 
| Quest 1 | Quest 2 | Quest 3 | Quest 4
Remote (virtual) | 70 | 88 | 90 | 85
On-site Microsoft KL | 20 | 10 | 8 | 10
On-site JCorp Johor | 10 | 2 | 2 | 5
Why this mix works
Reduces logistical burden
A 4-hour return KL-Johor commute per session is unsustainable for 12 months.
Preserves executive intimacy
Senior leaders get full in-person experience at Microsoft KL EBC - more impactful than any Johor visit.
Higher session frequency
Remote-first preserves consultant capacity, allowing weekly cadence rather than monthly.
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
7

## Slide 8
ENGAGEMENT MODEL
Cadence and channel by persona
Persona | Primary channel | Cadence | Format
Executive Leaders | On-site KL | Quarterly | Half-day immersion at Microsoft KL EBC
People Managers | Hybrid | Monthly | Virtual workshop + KL clinic per quarter
Knowledge Workers | Remote | Bi-weekly | Virtual labs + on-demand learning
Specialists | Remote | Monthly | Function-specific virtual deep-dives
Champions | Hybrid | Weekly | Virtual standups + quarterly KL bootcamp
Principle: Cadence is calibrated to role intensity. Champions and managers carry the weight of weekly engagement; broader population engages bi-weekly to monthly to avoid fatigue.
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
8

## Slide 9
THE JOURNEY
Four quests over twelve months
Each quest is a season - different focus, same energy
Q1
Lift-off
Months 1-3
Spark: sponsor, pilot, kick-off
Q2
Power Up
Months 4-6
Skill: onboard 200, train champions
Q3
Build Cool Stuff
Months 7-9
Build: hackathon, deep-dives
Q4
Soar & Celebrate
Months 10-12
Sustain: agents, finale, handover
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
9

## Slide 10
QUEST 1 OF 4
Lift-off
Months 1-3 | Spark phase
Q1
🎬 Kick-off!
1
Big launch party at JCorp HQ
Single Microsoft visit to Johor. Full HQ workforce energised. Sponsor publicly commits.
2
Leadership immersion at Microsoft KL
Half-day at the EBC. Demos, hands-on, peer conversations with other executives.
3
Pilot squad of 25 early adopters
Mix of champions and managers test-drive everything before broad rollout.
4
Readiness assessment & governance
M365 hygiene check, sensitivity labels, steering committee formed (JCorp + Microsoft).
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
10

## Slide 11
QUEST 2 OF 4
Power Up
Months 4-6 | Skill phase
Q2
🎓 Champions assemble!
1
All 200 teammates onboarded
Phased license rollout (50/month) with role-based virtual labs - 8 labs/week, max 25 learners each.
2
Champions bootcamp at Microsoft KL
1.5 days in person. Advanced Copilot, prompt craft, change management. Champions take it home.
3
Weekly Lunch & Learn sessions
60-minute virtual format. Real workflows, real wins. Recorded for the on-demand library.
4
First quarterly executive review
Senior Leadership returns to Microsoft KL to review adoption telemetry and shape Quest 3.
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
11

## Slide 12
QUEST 3 OF 4
Build Cool Stuff
Months 7-9 | Build phase
Q3
🏆 Hackathon time!
1
JCorp Copilot Hackathon
Cross-function teams co-design 5 JCorp-specific scenarios. Virtual build, KL judging.
2
Function-specific deep-dives
Virtual deep-dives for Finance, HR, Legal, Operations. Real artefacts, real value capture.
3
Mid-year roadshow in Johor
Microsoft team visits JCorp HQ. Listening tour, health check, momentum boost.
4
Live adoption leaderboard
Microsoft Adoption Score dashboard goes live. Friendly team-vs-team competition begins.
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
12

## Slide 13
QUEST 4 OF 4
Soar & Celebrate
Months 10-12 | Sustain phase
Q4
🎉 Celebrate!
1
Build your own AI agents
Advanced sessions on Copilot Studio, Pages, agent governance. JCorp-specific agents shipped.
2
Story showcase on camera
Teammates star in 60-second clips telling their best Copilot story. Library kept for year-2.
3
Year-end celebration in Johor
Microsoft visits JCorp HQ for the grand finale. Awards, case study readout, year-2 preview.
4
Champions take the wheel
JCorp owns the ongoing cadence. Microsoft steps into a sustained advisor role.
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
13

## Slide 14
CHAMPIONS NETWORK
15 internal heroes leading the charge
The always-on local presence that bridges the Johor-KL distance
Composition (15 total)
2 Executive Office / Strategy
3 Finance & Investments
2 Legal & Compliance
2 HR & People
2 Corporate Affairs
2 IT / Digital
2 Operations / Property
Time commitment
~4 hours per week (peer coaching)
1.5-day bootcamp at Microsoft KL
Quarterly retreat at Microsoft KL
Weekly virtual standup with MS Customer Success
Champion perks
Early access to new Copilot features
Public recognition by JCorp sponsor
Microsoft KL EBC experiences
Champion swag pack
Year-2 advisory role on Microsoft account team
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
14

## Slide 15
PRIORITY USE CASES
Top 10 JCorp-specific scenarios
Each paired with a champion, with measurable baselines taken before rollout
# | Use case | Function | Indicative value
1 | Board paper drafting & summarisation | Executive Office | 40-50% drafting time reduction
2 | Subsidiary performance roll-up analytics | Strategy / Finance | 2-4 hrs/analyst/week
3 | Meeting recap, actions and decisions | All managers | 30 min/meeting saved
4 | Investor & stakeholder briefing decks | Corporate Affairs | 50% deck-build time reduction
5 | Contract first-pass review | Legal | 1-2 hrs/contract
6 | HR policy Q&A & onboarding assistant | HR | Reduces HR ticket volume
7 | Email triage & response drafting | All employees | 30-45 min/day saved
8 | Tender / RFP response drafting | Business Development | 40% turnaround reduction
9 | Internal knowledge search | All employees | Faster onboarding, fewer 'who knows X' emails
10 | Sustainability / ESG report drafting | Corporate Affairs | Quarterly cycle compression
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
15

## Slide 16
ENGAGEMENT TACTICS
What keeps everyone hyped for 12 months
🏅
Badge collection
Earn digital badges for every milestone, shown in Teams profiles.
📊
Live leaderboard
Friendly team-vs-team adoption rankings. Bragging rights at stake.
🎙️
Copilot Confessions
Monthly podcast where teammates share their best (and weirdest) prompts.
🎂
Win-of-the-Week
Every Friday, one teammate's time-saving story gets celebrated org-wide.
🎨
Prompt remix challenges
Bi-weekly creative prompts. Best output gets featured and prized.
🍩
Donut sessions
Random pairings of teammates swap Copilot tips over a virtual coffee.
🎬
Story videos
60-sec clips showing how Copilot changed someone's week.
🏆
Quarterly awards
Best builder, best teacher, biggest impact - presented by the JCorp sponsor.
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
16

## Slide 17
SUCCESS SCORECARD
What 'winning' looks like by month 12
Tracked monthly via Microsoft Adoption Score and quarterly pulse surveys
KPI | Source | Q2 target | Q4 target
% licensed users active weekly | Adoption Score | 50% | 75%
Avg actions/user/week | Copilot telemetry | 15 | 30
Documented use cases with quantified value | Champions log | 5 | 10
Self-reported time saved (hrs/user/week) | Pulse survey | 3 | 5
Sentiment NPS (Copilot helpfulness) | Pulse survey | +30 | +50
Active champions in network | Roster + activity | 15 | 15
Training completion rate | Microsoft Learn / SharePoint | 70% | 90%
Integrity: Time-saved figures are self-reported and presented as such. Adoption Score and Copilot telemetry are objective. Where claims cannot be measured, they are flagged as assumptions.
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
17

## Slide 18
ADOPTION RAMP
Target trajectory: 75% weekly active by month 12
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
% weekly active users (target) | 5 | 10 | 15 | 25 | 40 | 55 | 62 | 68 | 72 | 74 | 75 | 78
Year 1 goal (75%) | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
18

## Slide 19
GOVERNANCE
Steering structure & decision rights
Body | Cadence | Membership | Format
Executive Steering Committee | Quarterly | JCorp sponsor + Microsoft account team | On-site KL EBC
Program Working Group | Bi-weekly | JCorp PMO + MS Customer Success | Teams (virtual)
Champions Council | Weekly | 15 champions + MS lead | Teams (virtual)
Technical Forum | Monthly | JCorp IT + MS FastTrack | Teams (virtual)
Decision rights
Strategic direction and budget
→ Executive Steering Committee
Operational delivery and content
→ Program Working Group
Use case prioritisation
→ Champions Council
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
19

## Slide 20
RISK REGISTER
Top 5 risks with mitigations
Risk | Likelihood | Impact | Mitigation
Remote engagement fatigue erodes attendance | Med | High | Cap virtual sessions at 60 min; gamify; champions drive peer accountability
Data hygiene gaps surface incorrect content | Med | High | Pre-rollout SharePoint permissions audit; sensitivity labels enforced
Executive sponsorship fades after kick-off | Med | High | Quarterly KL EBC sessions designed as executive-led, not vendor-led
License cost not justified by demonstrated value | Low | High | Quantified value capture from Q2 onwards; published quarterly
Champions burn out from overload | Med | Med | Time commitment formalised with line managers; recognition program
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
20

## Slide 21
INVESTMENT SUMMARY
Indicative effort and license envelope
Final pricing requires formal Microsoft commercial proposal
Chart: 
| Q1 Lift-off | Q2 Power Up | Q3 Build | Q4 Soar
Microsoft delivery (person-days) | 40 | 80 | 70 | 40
JCorp PMO + champions (person-days) | 30 | 90 | 100 | 70
Cost envelope
200x Copilot for M365 licenses
Annual commitment, JCorp procures direct or via partner
Microsoft enablement services
Largely covered through customer success investment; incremental scope quoted separately
JCorp travel (SLT to KL, quarterly)
Internal cost; estimated based on 8-12 travellers
Microsoft to JCorp Johor (3 visits/year)
Microsoft internal cost
Champions recognition & events
JCorp internal cost
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
21

## Slide 22
WHAT WE NEED FROM JCORP
Four decisions to unlock the program
1. Executive sponsor confirmed
Recommended: Chief HR Officer or Chief Digital Officer. ~2 hours/month commitment, plus quarterly KL EBC sessions.
2. 200 Copilot for M365 licenses approved
Annual commitment. JCorp procures direct or via Microsoft partner of choice.
3. 15 champions nominated
Across all functions, by end of month 1. Time commitment formalised with line managers.
4. Senior Leadership KL travel authorised
8-12 person SLT, quarterly trips to Microsoft KL EBC. Travel budget approved upfront.
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
22

## Slide 23
NEXT STEPS
Path from approval to kick-off
Week 1
1
Sponsor confirmation
JCorp executive sponsor signs off on scope and intent.
Weeks 2-3
2
Commercial proposal
Microsoft KL issues formal Customer Success Plan and license proposal.
Week 4
3
Champions nomination
Function leads nominate the 15 champions across JCorp HQ.
Weeks 5-6
4
Readiness assessment
MS FastTrack runs M365 hygiene check; sensitivity labels reviewed.
Week 7
5
Kick-off party in Johor
Microsoft visits JCorp HQ for the launch. Quest 1 begins.
Target kick-off: 7 weeks from JCorp executive sign-off.
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
23

## Slide 24
APPENDIX A
Full use case detail with Copilot surfaces
# | Use case | Copilot surface | Champion function
1 | Board paper drafting & summarisation | Word, Copilot Chat | Executive Office
2 | Subsidiary performance roll-up analytics | Excel, Copilot Chat | Strategy / Finance
3 | Meeting recap, actions and decisions | Teams | All managers
4 | Investor & stakeholder briefing decks | PowerPoint | Corporate Affairs
5 | Contract first-pass review | Word, Copilot Chat | Legal
6 | HR policy Q&A & onboarding assistant | Copilot Studio agent | HR
7 | Email triage & response drafting | Outlook | All employees
8 | Tender / RFP response drafting | Word, Copilot Chat | Business Development
9 | Internal knowledge search | Copilot Chat (work) | All employees
10 | Sustainability / ESG report drafting | Word, Excel | Corporate Affairs
JCorp x Microsoft Copilot | 12-Month Adoption Program | Confidential
24

## Slide 25
READY TO LAUNCH?
Let's go build it.
Confirm the sponsor. Nominate the champions. Set the kick-off date.
The adventure begins as soon as you say go.
Explore the live site
zeffree.github.io/jcorpmsft
Prepared by Microsoft Malaysia for Johor Corporation | Indicative figures subject to confirmation